## Work Log
Exascale — Project Work Log
Engagement start: 18/05/2026 · prepared 02/06/2026 · dates DD/MM/YYYY · fill the Agreed Price column
Task ID | Date | Phase | Task / Deliverable | Status | Agreed Price
1 | 18/05/2026 | 1 · Discovery | Project briefing & scope intake — Exascale: a commodity market for AI compute (three-sided market: datacenters · traders · AI companies) | Done
2 | 18/05/2026 | 1 · Discovery | Market & product research — version 1 (concept, competitors, positioning, references) | Done
3 | 19/05/2026 | 1 · Discovery | Market & product research — version 2 (refined direction, scope & feature map) | Done
4 | 20/05/2026 | 1 · Discovery | Research write-up & direction confirmation (sign-off before build) | Done
5 | 21/05/2026 | 2 · Brand | Brand book — visual identity, design tokens, color, typography, components (brand-book.css / .html / print) | Done
6 | 21/05/2026 | 2 · Brand | Brand book — interactive theme / tweaks panel (live token editor) | Done
7 | 22/05/2026 | 3 · Structure | MVP screen catalog & per-screen prompt structure — 26 screens across 3 tiers (exascale_mvp_screens_prompts.md) | Done
8 | 22/05/2026 | 3 · Structure | MVP screens checklist & coverage tracker | Done
9 | 22/05/2026 | 4 · Design | Screen design — Landing / homepage (Tier 1) | Done
10 | 22/05/2026 | 4 · Design | Screen design — Trading dashboard, the headline (Tier 1) | Done
11 | 23/05/2026 | 4 · Design | Screen design — Market detail (Tier 1) | Done
12 | 23/05/2026 | 4 · Design | Screen design — Credit wallet (Tier 1) | Done
13 | 23/05/2026 | 4 · Design | Screen design — Index methodology page (Tier 1) | Done
14 | 23/05/2026 | 4 · Design | Screen design — Signup (Tier 2) | Done
15 | 23/05/2026 | 4 · Design | Screen design — KYC light flow (Tier 2) | Done
16 | 23/05/2026 | 4 · Design | Screen design — Portfolio (Tier 2) | Done
17 | 23/05/2026 | 4 · Design | Screen design — Trade history (Tier 2) | Done
18 | 23/05/2026 | 4 · Design | Screen design — Buy credits flow (Tier 2) | Done
19 | 24/05/2026 | 4 · Design | Screen design — Enterprise onboarding (Tier 2) | Done
20 | 24/05/2026 | 4 · Design | Screen design — Team & sub-accounts (Tier 2) | Done
21 | 24/05/2026 | 4 · Design | Screen design — Compute instances list (Tier 2) | Done
22 | 24/05/2026 | 4 · Design | Screen design — Create instance flow (Tier 2) | Done
23 | 24/05/2026 | 4 · Design | Screen design — Inference playground + model catalog (Tier 2) | Done
24 | 24/05/2026 | 4 · Design | Screen design — Login (Tier 3) | Done
25 | 24/05/2026 | 4 · Design | Screen design — Email verification + welcome (Tier 3) | Done
26 | 24/05/2026 | 4 · Design | Screen design — Audit log (Tier 3) | Done
27 | 24/05/2026 | 4 · Design | Screen design — Billing dashboard (Tier 3) | Done
28 | 24/05/2026 | 4 · Design | Screen design — DC partner dashboard (Tier 3) | Done
29 | 24/05/2026 | 4 · Design | Screen design — Partner capacity registration (Tier 3) | Done
30 | 24/05/2026 | 4 · Design | Screen design — Settings shell (Tier 3) | Done
31 | 24/05/2026 | 4 · Design | Screen design — API keys settings (Tier 3) | Done
32 | 24/05/2026 | 4 · Design | Screen design — Notifications drawer (Tier 3) | Done
33 | 24/05/2026 | 4 · Design | Screen design — Command palette (Cmd+K) (Tier 3) | Done
34 | 24/05/2026 | 4 · Design | Screen design — Empty / loading / error states (Tier 3) | Done
35 | 24/05/2026 | 5 · Frontend | Nuxt 4 + Vue 3 + TypeScript project setup; design-token migration; HTML->Nuxt migration plan | Done
36 | 25/05/2026 | 5 · Frontend | Frontend — marketing homepage (index) + benchmark / index-methodology page | Done
37 | 25/05/2026 | 5 · Frontend | Frontend — auth screens: login, signup | Done
38 | 25/05/2026 | 5 · Frontend | Frontend — onboarding flow: welcome, email verify, KYC, tour | Done
39 | 25/05/2026 | 5 · Frontend | Frontend — trading dashboard (trade) | Done
40 | 26/05/2026 | 5 · Frontend | Frontend — markets: list + market detail | Done
41 | 26/05/2026 | 5 · Frontend | Frontend — portfolio + trade history | Done
42 | 26/05/2026 | 5 · Frontend | Frontend — wallet: balances + buy credits | Done
43 | 26/05/2026 | 5 · Frontend | Frontend — compute: instances list, create instance, instance detail | Done
44 | 26/05/2026 | 5 · Frontend | Frontend — inference playground + model catalog | Done
45 | 27/05/2026 | 5 · Frontend | Frontend — console (dense institutional dashboard) | Done
46 | 27/05/2026 | 5 · Frontend | Frontend — enterprise: onboarding, teams, audit, billing, SSO | Done
47 | 27/05/2026 | 5 · Frontend | Frontend — datacenter partner: dashboard, capacity registration | Done
48 | 27/05/2026 | 5 · Frontend | Frontend — settings shell + API keys; status page; UI states | Done
49 | 27/05/2026 | 5 · Frontend | Frontend — shared app shell: sidebar, topbar, command palette, notifications, toasts | Done
50 | 27/05/2026 | 6 · v1.5 | v1.5 screens catalog & gap analysis (post-MVP, exascale_v15_screens_prompts.md) | Done
51 | 28/05/2026 | 6 · v1.5 | v1.5 build — trading-depth + money-operations screens | Done
52 | 28/05/2026 | 6 · v1.5 | v1.5 build — compute/inference v1.5 + enterprise-depth screens | Done
53 | 28/05/2026 | 6 · v1.5 | v1.5 build — datacenter, marketing/public/developer, admin, help/error/mobile states | Done
54 | 28/05/2026 | 7 · Tour | Guided product tour — click-through (tour engine, tour scripts, help-dot rollout) | Done
55 | 28/05/2026 | 7 · Tour | Product tour — auto-play / video tour mode | Done
56 | 28/05/2026 | 8 · Deploy | Netlify deployment — static generate + hosting configuration | Done
57 | 28/05/2026 | 8 · Deploy | DNS configuration (custom domain) | Done
58 | 28/05/2026 | 8 · Deploy | Frontend password protection (gated preview access) | Done
59 | 29/05/2026 | 9 · Demo | Investor narrative & demo source pack (NotebookLM) | Done
60 | 29/05/2026 | 9 · Demo | 3-minute investor video script + UI walkthrough shot list | Done
61 | 29/05/2026 | 9 · Demo | Demo video production / montage (edit + voice-over sync) | Done
62 | 29/05/2026 | 10 · Platform | Platform-first build plan, management plan, sequencing & engineering standards (docs/plans) | Done
63 | 29/05/2026 | 10 · Platform | Multi-agent delivery system — 13-agent roster + shared contracts (OpenAPI / SQL / events / credit-types) | Done
64 | 29/05/2026 | 10 · Platform | F01 — Foundation infra: k3d cluster + data plane (Postgres / TimescaleDB / Redis / NATS) + CI scaffold | Done
65 | 29/05/2026 | 10 · Platform | F05 — Prepaid credit ledger: append-only hash chain, fixed-point money, atomic & idempotent (v0.1.0) | Done
66 | 30/05/2026 | 10 · Platform | F02 — Auth & SSO: signup / login -> JWT, API keys, bcrypt; live cross-service auth (v0.1.1) | Done
67 | 30/05/2026 | 10 · Platform | F08 — Inference gateway: OpenAI-compatible API, API-key auth, usage metering (v0.2.0) | Done
68 | 30/05/2026 | 10 · Platform | F06 — Credit purchase / billing: Stripe checkout -> webhook -> idempotent ledger mint (v0.2.1) | Done
69 | 30/05/2026 | 10 · Platform | F09 — vLLM runtime integration: gateway<->runtime + CPU stub (v0.2.2) | Done
70 | 30/05/2026 | 10 · Platform | F20 — Platform console: BFF (mock->live seam) + live /console dashboard (v0.2.3) | Done
71 | 30/05/2026 | 10 · Platform | F03 — Accounts / orgs / RBAC + queryable audit log (v0.1.2) | Done
72 | 30/05/2026 | 10 · Platform | Gap-closers — email verification + monthly budgets + endpoint wiring (v0.1.3) | Done
73 | 30/05/2026 | 10 · Platform | F07 — Credit conversion: AI-index <-> text, atomic two-leg, 1% spread (v0.2.4) | Done
74 | 31/05/2026 | 10 · Platform | F04 — exascale CLI: login / credits / catalog / infer / keys (v0.1.4, + --password v0.1.5) | Done
75 | 31/05/2026 | 10 · Platform | F20xF07 — wallet convert drawer executes live conversions (v0.2.5) | Done
76 | 31/05/2026 | 10 · Platform | F20xF05 — wallet recent-movements renders live ledger transactions (v0.2.6) | Done
77 | 31/05/2026 | 10 · Platform | F20xF08 — inference credit meter + fixed inference-debit flow (push->pull consumer) (v0.2.7) | Done
78 | 31/05/2026 | 10 · Platform | F20xF02 — settings API keys manage live platform-core keys (v0.2.8) | Done
79 | 31/05/2026 | 10 · Platform | Local email via Mailpit + persona-scoped navigation (v0.2.9) | Done
80 | 31/05/2026 | 10 · Platform | Persona-aware onboarding — trader KYC vs AI-company vs datacenter (v0.2.10) | Done
81 | 31/05/2026 | 10 · Platform | Feature specs & designs for remaining roadmap — F10-F19 (catalog, packing, GPU lifecycle, clusters, supply, payouts, attestation), F21 SOC2, F22 licensing, KW01-05 (index/trading/matching/market-maker/surveillance) | Done (specced)
82 | 01/06/2026 | 10 · Platform | Documentation — RUN_LOCAL, TESTING (per-persona), DEPLOYMENT, PROVISIONING, PLATFORM_GAPS | Done
TOTAL |  |  | 82 tasks